## Burndown Summary
| (SP) Added | (SP) Commited | (SP) Done | Burnt Carries (US) | (SP) Burnt | (SP) Total | (SP) Remain to Burn
3 | 21 | 0 | 0 | 0 | 0 | 21 | 21
4 | 144 | 0 | 0 | 0 | 0 | 165 | 165
5 | 110 | 110 | 0 | 0 | 0 | 275 | 275
9 | 34 | 0 | 0 | 0 | 0 | 309 | 309
10 | 186 | 21 | 0 | 0 | 0 | 495 | 495
11 | 359 | 301 | 21 | 1 | 21 | 854 | 833
12 | 0 | 228 | 0 | 0 | 21 | 854 | 833
13 | 8 | 131 | 139 | 6 | 160 | 862 | 702
14 | 68 | 0 | 390 | 10 | 550 | 930 | 380
15 | 42 | 131 | 21 | 1 | 571 | 972 | 401
16 | 107 | 94 | 186 | 9 | 757 | 1079 | 322
17 | 152 | 199 | 60 | 5 | 817 | 1231 | 414
18 | 5 | 21 | 204 | 6 | 1021 | 1236 | 215

## Data
Sprint (Jira) | Status | Issue Key | Story Points (Original) | Story Points (Real) | Backlog Sprint | Dev Begin Sprint | Dev End Sprint | Dev Carry | QA Begin Sprint | QA End Sprint | QA Carry | Epic | Created | Dev Begin (In Development) | Dev End (Ready for Build) | Days in Dev | QA Begin (In QA) | QA End (QA Done) | Days in QA
Sprint 11 | READY | NCIS-261 |  | 55 | 5 | 5 | 14 | 9 | 18 | 18 | 0 | NCIS-240 | 2019-03-11 | 2019-03-13 | 2019-07-12 | 121 | 2019-09-09 | 2019-09-10 | 1
Sprint 11 | READY | NCIS-262 |  | 55 | 5 | 5 | 14 | 9 | 17 | 18 | 1 | NCIS-240 | 2019-03-11 | 2019-03-15 | 2019-07-12 | 119 | 2019-08-29 | 2019-09-10 | 12
Sprint 11 | READY | NCIS-333 |  | 34 | 9 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-179 | 2019-05-09 | 2019-05-29 | 2019-07-08 | 40 | 2019-07-15 | 2019-07-18 | 3
Sprint 11 | READY | NCIS-349 |  | 21 | 10 | 10 | 11 | 1 | 12 | 13 | 1 | NCIS-221 | 2019-05-15 | 2019-05-15 | 2019-06-06 | 22 | 2019-06-10 | 2019-07-02 | 22
Sprint 11 | READY | NCIS-391 |  | 34 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-179 | 2019-05-28 | 2019-06-03 | 2019-07-08 | 35 | 2019-07-15 | 2019-07-18 | 3
Sprint 11 | READY | NCIS-392 |  | 21 | 11 | 11 | 13 | 2 | 14 | 14 | 0 | NCIS-179 | 2019-05-28 | 2019-06-04 | 2019-07-02 | 28 | 2019-07-15 | 2019-07-18 | 3
Sprint 11 | READY | NCIS-393 |  | 55 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-05-28 | 2019-07-12 | 45 | 2019-07-15 | 2019-07-16 | 1
Sprint 11 | READY | NCIS-394 |  | 34 | 11 | 11 | 13 | 2 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-05-30 | 2019-07-02 | 33 | 2019-07-15 | 2019-07-16 | 1
Sprint 11 | READY | NCIS-396 |  | 21 | 11 | 11 | 13 | 2 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-06-05 | 2019-07-02 | 27 | 2019-07-15 | 2019-07-16 | 1
Sprint 11 | READY | NCIS-397 |  | 34 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-06-04 | 2019-07-12 | 38 | 2019-07-15 | 2019-07-18 | 3
Sprint 11 | READY | NCIS-398 |  | 34 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-06-07 | 2019-07-12 | 35 | 2019-07-15 | 2019-07-16 | 1
Sprint 11 | READY | NCIS-404 |  | 34 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-221 | 2019-06-04 | 2019-06-05 | 2019-07-12 | 37 | 2019-07-15 | 2019-07-16 | 1
Sprint 12 | IN-QA | NCIS-232 |  | 55 | 4 | 12 | 18 | 6 | 18 | #N/A | #N/A | NCIS-240 | 2019-02-20 | 2019-06-12 | 2019-09-04 | 84 | 2019-09-11 |  | 0
Sprint 12 | READY | NCIS-406 |  | 21 | 11 | 12 | 13 | 1 | 17 | 18 | 1 | NCIS-418 | 2019-06-04 | 2019-06-17 | 2019-07-03 | 16 | 2019-08-29 | 2019-09-09 | 11
Sprint 12 | READY | NCIS-413 |  | 21 | 11 | 12 | 13 | 1 | 17 | 18 | 1 | NCIS-421 | 2019-06-06 | 2019-06-12 | 2019-07-03 | 21 | 2019-08-29 | 2019-09-09 | 11
Sprint 12 | READY | NCIS-415 | 8 | 21 | 11 | 15 | 16 | 1 | 17 | 18 | 1 | NCIS-179 | 2019-06-06 | 2019-07-31 | 2019-08-16 | 16 | 2019-08-29 | 2019-09-10 | 12
Sprint 12 | READY | NCIS-416 | 3 | 21 | 11 | 12 | 14 | 2 | 17 | 18 | 1 | NCIS-418 | 2019-06-06 | 2019-06-17 | 2019-07-12 | 25 | 2019-08-29 | 2019-09-10 | 12
Sprint 12 | OPEN | NCIS-417 |  | #N/A | 11 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-418 | 2019-06-06 |  |  | 0 |  |  | 0
Sprint 14 | READY | NCIS-176 |  | 21 | 3 | 12 | 13 | 1 | 14 | 14 | 0 | NCIS-418 | 2019-02-12 | 2019-06-10 | 2019-07-02 | 22 | 2019-07-15 | 2019-07-17 | 2
Sprint 14 | READY | NCIS-220 |  | 34 | 4 | 12 | 14 | 2 | 14 | 14 | 0 | NCIS-418 | 2019-02-20 | 2019-06-11 | 2019-07-12 | 31 | 2019-07-15 | 2019-07-19 | 4
Sprint 15 | READY | NCIS-214 |  | 55 | 4 | 12 | 16 | 4 | 17 | 17 | 0 | NCIS-239 | 2019-02-20 | 2019-06-19 | 2019-08-16 | 58 | 2019-08-22 | 2019-08-27 | 5
Sprint 15 | READY | NCIS-450 |  | 13 | 10 | 15 | 16 | 1 | 17 | 18 | 1 | NCIS-448 | 2019-06-22 | 2019-07-23 | 2019-08-05 | 13 | 2019-08-29 | 2019-09-09 | 11
Sprint 15 | READY | NCIS-451 | 3 | 21 | 10 | 15 | 16 | 1 | 17 | 18 | 1 | NCIS-448 | 2019-06-22 | 2019-07-31 | 2019-08-16 | 16 | 2019-08-29 | 2019-09-09 | 11
Sprint 15 | READY | NCIS-453 | 8 | 21 | 10 | 13 | 15 | 2 | 15 | 15 | 0 | NCIS-448 | 2019-06-22 | 2019-07-03 | 2019-07-23 | 20 | 2019-07-23 | 2019-07-23 | 0
Sprint 15 | READY | NCIS-495 |  | 21 | 14 | 15 | 16 | 1 | 17 | #N/A | #N/A | NCIS-543 | 2019-07-10 | 2019-07-23 | 2019-08-16 | 24 | 2019-08-29 |  | 13
Sprint 15 | READY | NCIS-499 |  | 13 | 14 | 15 | 16 | 1 | #N/A | #N/A | #N/A | NCIS-637 | 2019-07-12 | 2019-08-01 | 2019-08-16 | 15 |  |  | 0
Sprint 15 | READY | NCIS-501 |  | 13 | 14 | 15 | 16 | 1 | #N/A | #N/A | #N/A | NCIS-588 | 2019-07-12 | 2019-08-01 | 2019-08-16 | 15 |  |  | 0
Sprint 15 | BA-SO | NCIS-502 | 3 | 8 | 14 | 15 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-618 | 2019-07-12 | 2019-09-02 |  | 9 |  |  | 0
Sprint 15 | READY | NCIS-516 |  | 21 | 15 | 15 | 16 | 1 | 17 | 18 | 1 | NCIS-699 | 2019-07-25 | 2019-07-25 | 2019-08-15 | 21 | 2019-08-22 | 2019-09-03 | 12
Sprint 15 | BA-SO | NCIS-522 | 5 | 21 | 15 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-593 | 2019-07-28 | 2019-08-20 |  | 22 |  |  | 0
Sprint 16 | READY | NCIS-419 | 5 | 8 | 11 | 16 | 16 | 0 | 17 | 18 | 1 | NCIS-179 | 2019-06-07 | 2019-08-09 | 2019-08-16 | 7 | 2019-08-22 | 2019-09-03 | 12
Sprint 16 | IN-QA | NCIS-455 | 3 | 55 | 10 | 13 | 18 | 5 | 18 | #N/A | #N/A | NCIS-448 | 2019-06-22 | 2019-06-26 | 2019-09-03 | 69 | 2019-09-11 |  | 0
Sprint 16 | IN-QA | NCIS-456 | 5 | 55 | 10 | 13 | 18 | 5 | 18 | #N/A | #N/A | NCIS-448 | 2019-06-22 | 2019-07-02 | 2019-09-03 | 63 | 2019-09-11 |  | 0
Sprint 16 | IN-DEV | NCIS-527 |  | 21 | 16 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-504 | 2019-08-05 | 2019-08-19 |  | 23 |  |  | 0
Sprint 16 | IN-DEV | NCIS-538 |  | 34 | 16 | 16 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-530 | 2019-08-05 | 2019-08-05 |  | 37 |  |  | 0
Sprint 16 | READY | NCIS-539 |  | 13 | 16 | 16 | 17 | 1 | 17 | 17 | 0 | NCIS-530 | 2019-08-05 | 2019-08-05 | 2019-08-20 | 15 | 2019-08-29 | 2019-08-29 | 0
Sprint 16 | READY | NCIS-540 |  | 13 | 16 | 16 | 17 | 1 | 17 | 17 | 0 | NCIS-530 | 2019-08-05 | 2019-08-05 | 2019-08-20 | 15 | 2019-08-29 | 2019-08-29 | 0
Sprint 16 | READY | NCIS-541 |  | 13 | 16 | 16 | 17 | 1 | 17 | 17 | 0 | NCIS-530 | 2019-08-05 | 2019-08-05 | 2019-08-20 | 15 | 2019-08-29 | 2019-08-29 | 0
Sprint 17 | IN-QA | NCIS-491 | 5 | 13 | 14 | 17 | 18 | 1 | 18 | #N/A | #N/A | NCIS-678 | 2019-07-09 | 2019-08-19 | 2019-09-03 | 15 | 2019-09-11 |  | 0
Sprint 17 | BLOCK | NCIS-542 |  | 13 | 16 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 2019-08-06 | 2019-08-29 |  | 13 |  |  | 0
Sprint 17 | IN-QA | NCIS-561 | 2 | 13 | 17 | 17 | 18 | 1 | 18 | #N/A | #N/A | NCIS-560 | 2019-08-19 | 2019-08-19 | 2019-09-03 | 15 | 2019-09-10 |  | 1
Sprint 17 | IN-QA | NCIS-562 | 1 | 13 | 17 | 17 | 18 | 1 | 18 | #N/A | #N/A | NCIS-560 | 2019-08-19 | 2019-08-22 | 2019-09-03 | 12 | 2019-09-10 |  | 1
Sprint 17 | IN-QA | NCIS-563 |  | 8 | 17 | 17 | 17 | 0 | 18 | #N/A | #N/A | NCIS-691 | 2019-08-19 | 2019-08-20 | 2019-08-27 | 7 | 2019-09-11 |  | 0
Sprint 17 | BLOCK | NCIS-564 |  | 21 | 17 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 2019-08-19 | 2019-08-22 |  | 20 |  |  | 0
Sprint 17 | BA-SO | NCIS-565 | 8 | 21 | 17 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-648 | 2019-08-19 | 2019-08-20 |  | 22 |  |  | 0
Sprint 17 | BA-SO | NCIS-568 | 5 | 21 | 17 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-552 | 2019-08-20 | 2019-08-20 |  | 22 |  |  | 0
Sprint 17 | NO-DEV | NCIS-572 |  | #N/A | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-571 | 2019-08-20 |  |  | 0 |  |  | 0
Sprint 17 | IN-DEV | NCIS-574 | 3 | 21 | 17 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-234 | 2019-08-21 | 2019-08-21 |  | 21 |  |  | 0
Sprint 17 | NO-DEV | NCIS-577 |  | 21 | 17 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 2019-08-22 | 2019-08-23 |  | 19 |  |  | 0
Sprint 17 | IN-DEV | NCIS-578 | 3 | 21 | 17 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-235 | 2019-08-23 | 2019-08-23 |  | 19 |  |  | 0
Sprint 17 | IN-DEV | NCIS-581 | 5 | 13 | 17 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-659 | 2019-08-26 | 2019-08-27 |  | 15 |  |  | 0
Sprint 17 | BA-SO | NCIS-760 | 2 | 5 | 18 | 18 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-659 | 2019-09-03 | 2019-09-06 |  | 5 |  |  | 0
Sprint 18 | IN-DEV | NCIS-470 | 5 | 8 | 13 | 18 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-504 | 2019-06-28 | 2019-09-05 |  | 6 |  |  | 0
Sprint 18 | READY | NCIS-551 |  | 13 | 16 | 16 | 17 | 1 | 18 | 18 | 0 | NCIS-744 | 2019-08-13 | 2019-08-15 | 2019-08-28 | 13 | 2019-09-10 | 2019-09-11 | 1
Sprint 18 | OPEN | NCIS-745 | 8 | #N/A | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-576 | 2019-08-28 |  |  | 0 |  |  | 0
Sprint 18 | IN-DEV | NCIS-749 | 3 | 13 | 17 | 17 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-553 | 2019-08-28 | 2019-08-28 |  | 14 |  |  | 0
Sprint 18 | IN-DEV | NCIS-754 | 3 | 5 | 17 | 18 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-699 | 2019-08-30 | 2019-09-06 |  | 5 |  |  | 0
Sprint 18 | IN-DEV | NCIS-757 | 5 | 3 | 17 | 18 | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-571 | 2019-08-30 | 2019-09-09 |  | 2 |  |  | 0
Sprint 18 | OPEN | NCIS-761 | 5 | #N/A | 18 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-744 | 2019-09-03 |  |  | 0 |  |  | 0
Formulas:
Days in Dev = IF(ISBLANK([Dev End (Ready for Build)]), IF(ISBLANK([Dev Begin (In Development)]),0, TODAY()-[Dev Begin (In Development)]), [Dev End (Ready for Build)]-[Dev Begin (In Development)])
Days in QA = IF(ISBLANK([QA End (QA Done)]), IF(ISBLANK([QA Begin (In QA)]),0,TODAY()-[QA Begin (In QA)]), [QA End (QA Done)]-[QA Begin (In QA)])

## SP
From | To | Story Points
1 | 1 | 1
2 | 3 | 3
4 | 5 | 5
6 | 10 | 8
11 | 15 | 13
16 | 30 | 21
31 | 40 | 34
41 | 100 | 55

## Sprints
From | To | Sprints
2019-01-07 | 2019-01-18 | 1
2019-01-21 | 2019-02-01 | 2
2019-02-04 | 2019-02-15 | 3
2019-02-18 | 2019-03-01 | 4
2019-03-04 | 3/15/2019 | 5
2019-03-18 | 3/29/2019 | 6
2019-04-01 | 2019-04-12 | 7
2019-04-15 | 2019-04-26 | 8
2019-04-29 | 5/10/2'19 | 9
2019-05-13 | 5/24/2019 | 10
2019-05-28 | 2019-06-07 | 11
2019-06-10 | 2019-06-21 | 12
2019-06-24 | 2019-07-05 | 13
2019-07-08 | 2019-07-19 | 14
2019-07-22 | 8/2/2019 | 15
2019-08-05 | 2019-08-16 | 16
2019-08-19 | 2019-08-30 | 17
2019-09-03 | 2019-09-13 | 18
2019-09-11 | 2019-09-11 | 18