## Burndown Summary
DEV | (SP) Added | (SP) Commited | (SP) Done | Carried (US) | (SP) Burnt | (SP) Total | (SP) Remain to Burn | QA | Backlog Sprint | (SP) Commited | (SP) Done | Carried (US) | (SP) Burnt | (SP) Total | (SP) Remain to Burn
Sprint 1 | 25 | 25 | 11 | 0 | 11 | 25 | 14 | Sprint 1 | 25 | 0 | 0 | 0 | 0 | 25 | 25
Sprint 2 | 3 | 3 | 14 | 1 | 25 | 28 | 3 | Sprint 2 | 3 | 17 | 14 | 0 | 14 | 28 | 14
Sprint 3 | 5 | 5 | 8 | 2 | 33 | 33 | 0 | Sprint 3 | 5 | 8 | 11 | 1 | 25 | 33 | 8
[8 empty] | Sprint 4 | 0 | 8 | 8 | 0 | 33 | 33 | 0

## Data
| Issue Key | Story Points (Original) | Story Points (Real) | Backlog Sprint | Dev Begin Sprint | Dev End Sprint | Dev Carry | QA Begin Sprint | QA End Sprint | QA Carry | Epic | Created | Dev Begin (In Development) | Dev End (Ready for Build) | Days in Dev | QA Begin (In QA) | QA End (QA Done) | Days in QA
Sprint 11 | NCIS-261 |  | 55 | 5 | 5 | 14 | 9 | 18 | #N/A | #N/A | NCIS-240 | 2019-03-11 | 2019-03-13 | 2019-07-12 | 121 | 2019-09-09 |  | 1
Sprint 11 | NCIS-262 |  | 55 | 5 | 5 | 14 | 9 | 17 | #N/A | #N/A | NCIS-240 | 2019-03-11 | 2019-03-15 | 2019-07-12 | 119 | 2019-08-29 |  | 12
Sprint 11 | NCIS-333 |  | 34 | 9 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-179 | 2019-05-09 | 2019-05-29 | 2019-07-08 | 40 | 2019-07-15 | 2019-07-18 | 3
Sprint 11 | NCIS-349 |  | 21 | 10 | 10 | 11 | 1 | 12 | 13 | 1 | NCIS-221 | 2019-05-15 | 2019-05-15 | 2019-06-06 | 22 | 2019-06-10 | 2019-07-02 | 22
Sprint 11 | NCIS-391 |  | 34 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-179 | 2019-05-28 | 2019-06-03 | 2019-07-08 | 35 | 2019-07-15 | 2019-07-18 | 3
Sprint 11 | NCIS-392 |  | 21 | 11 | 11 | 13 | 2 | 14 | 14 | 0 | NCIS-179 | 2019-05-28 | 2019-06-04 | 2019-07-02 | 28 | 2019-07-15 | 2019-07-18 | 3
Sprint 11 | NCIS-393 |  | 55 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-05-28 | 2019-07-12 | 45 | 2019-07-15 | 2019-07-16 | 1
Sprint 11 | NCIS-394 |  | 34 | 11 | 11 | 13 | 2 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-05-30 | 2019-07-02 | 33 | 2019-07-15 | 2019-07-16 | 1
Sprint 11 | NCIS-396 |  | 21 | 11 | 11 | 13 | 2 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-06-05 | 2019-07-02 | 27 | 2019-07-15 | 2019-07-16 | 1
Sprint 11 | NCIS-397 |  | 34 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-06-04 | 2019-07-12 | 38 | 2019-07-15 | 2019-07-18 | 3
Sprint 11 | NCIS-398 |  | 34 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-221 | 2019-05-28 | 2019-06-07 | 2019-07-12 | 35 | 2019-07-15 | 2019-07-16 | 1
Sprint 11 | NCIS-404 |  | 34 | 11 | 11 | 14 | 3 | 14 | 14 | 0 | NCIS-221 | 2019-06-04 | 2019-06-05 | 2019-07-12 | 37 | 2019-07-15 | 2019-07-16 | 1
Sprint 12 | NCIS-232 |  | 55 | 4 | 12 | 18 | 6 | #N/A | #N/A | #N/A | NCIS-240 | 2019-02-20 | 2019-06-12 | 2019-09-04 | 84 |  |  | 0
Sprint 12 | NCIS-406 |  | 21 | 11 | 12 | 13 | 1 | 17 | 18 | 1 | NCIS-418 | 2019-06-04 | 2019-06-17 | 2019-07-03 | 16 | 2019-08-29 | 2019-09-09 | 11
Sprint 12 | NCIS-413 |  | 21 | 11 | 12 | 13 | 1 | 17 | 18 | 1 | NCIS-421 | 2019-06-06 | 2019-06-12 | 2019-07-03 | 21 | 2019-08-29 | 2019-09-09 | 11
Sprint 12 | NCIS-415 | 8 | 21 | 11 | 15 | 16 | 1 | 17 | 18 | 1 | NCIS-179 | 2019-06-06 | 2019-07-31 | 2019-08-16 | 16 | 2019-08-29 | 2019-09-10 | 12
Sprint 12 | NCIS-416 | 3 | 21 | 11 | 12 | 14 | 2 | 17 | 18 | 1 | NCIS-418 | 2019-06-06 | 2019-06-17 | 2019-07-12 | 25 | 2019-08-29 | 2019-09-10 | 12
Sprint 12 | NCIS-417 |  | #N/A | 11 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | NCIS-418 | 2019-06-06 |  |  | 0 |  |  | 0
Sprint 14 | NCIS-176 |  | 21 | 3 | 12 | 13 | 1 | 14 | 14 | 0 | NCIS-418 | 2019-02-12 | 2019-06-10 | 2019-07-02 | 22 | 2019-07-15 | 2019-07-17 | 2
Sprint 14 | NCIS-220 |  | 34 | 4 | 12 | 14 | 2 | 14 | 14 | 0 | NCIS-418 | 2019-02-20 | 2019-06-11 | 2019-07-12 | 31 | 2019-07-15 | 2019-07-19 | 4
Formulas:
Days in QA = IF(ISBLANK([QA End (QA Done)]), IF(ISBLANK([QA Begin (In QA)]),0,TODAY()-[QA Begin (In QA)]), [QA End (QA Done)]-[QA Begin (In QA)])

## SP
From | To | Story Points
1 | 1 | 1
2 | 3 | 3
4 | 5 | 5
6 | 10 | 8
11 | 15 | 13
16 | 30 | 21
31 | 40 | 34
41 | 100 | 55

## Sprints
From | To | Sprints
2019-01-07 | 2019-01-18 | 1
2019-01-21 | 2019-02-01 | 2
2019-02-04 | 2019-02-15 | 3
2019-02-18 | 2019-03-01 | 4
2019-03-04 | 3/15/2019 | 5
2019-03-18 | 3/29/2019 | 6
2019-04-01 | 2019-04-12 | 7
2019-04-15 | 2019-04-26 | 8
2019-04-29 | 5/10/2'19 | 9
2019-05-13 | 5/24/2019 | 10
2019-05-28 | 2019-06-07 | 11
2019-06-10 | 2019-06-21 | 12
2019-06-24 | 2019-07-05 | 13
2019-07-08 | 2019-07-19 | 14
2019-07-22 | 8/2/2019 | 15
2019-08-05 | 2019-08-16 | 16
2019-08-19 | 2019-08-30 | 17
2019-09-03 | 2019-09-13 | 18
2019-09-10 | 2019-09-10 | 18