## Burndown Summary
DEV | (SP) Added | (SP) Commited | (SP) Done | Carried (US) | (SP) Total | (SP) Burnt | QA | Backlog Sprint | (SP) Commited | (SP) Done | Carried (US) | (SP) Total | (SP) Burnt
Sprint 1 | 25 | 25 | 11 | 0 | 25 | 25 | Sprint 1 | 25 | 0 | 0 | 0 | 25 | 25
Sprint 2 | 3 | 3 | 14 | 1 | 28 | 17 | Sprint 2 | 3 | 17 | 14 | 0 | 28 | 28
Sprint 3 | 5 | 5 | 8 | 2 | 33 | 19 | Sprint 3 | 5 | 8 | 11 | 1 | 33 | 19
[7 empty] | Sprint 4 | 0 | 8 | 8 | 0 | 33 | 22

## Data
Issue key | Story Points | Backlog Sprint | Dev Begin Sprint | Dev End Sprint | Dev Carry | QA Begin Sprint | QA End Sprint | QA Carry
1 | 3 | NCIS Sprint 1 | NCIS Sprint 1 | NCIS Sprint 1 | 0 | NCIS Sprint 2 | NCIS Sprint 2 | 0
2 | 3 | NCIS Sprint 1 | NCIS Sprint 1 | NCIS Sprint 1 | 0 | NCIS Sprint 2 | NCIS Sprint 2 | 0
3 | 5 | NCIS Sprint 1 | NCIS Sprint 1 | NCIS Sprint 1 | 0 | NCIS Sprint 2 | NCIS Sprint 2 | 0
4 | 8 | NCIS Sprint 1 | NCIS Sprint 1 | NCIS Sprint 2 | 1 | NCIS Sprint 3 | NCIS Sprint 3 | 0
5 | 3 | NCIS Sprint 1 | NCIS Sprint 1 | NCIS Sprint 2 | 0 | NCIS Sprint 2 | NCIS Sprint 2 | 0
5 | 3 | NCIS Sprint 1 | NCIS Sprint 1 | NCIS Sprint 3 | 2 | NCIS Sprint 2 | NCIS Sprint 3 | 1
6 | 3 | NCIS Sprint 2 | NCIS Sprint 2 | NCIS Sprint 2 | 0 | NCIS Sprint 4 | NCIS Sprint 4 | 0
7 | 5 | NCIS Sprint 3 | NCIS Sprint 3 | NCIS Sprint 3 | 0 | NCIS Sprint 4 | NCIS Sprint 4 | 0